## Slide 1: RADIS Project Report
Prepared by: Kelsey Hilton

## Slide 2: Agenda
Project Overview
Milestones Summary
Outstanding Issues
Status Review
Next Steps

## Slide 3: Project Overview
Project description
  Develop an API that can be used to process images for medical diagnostic applications
  Hendrick Medical Center requires a new Radiological Application for Diagnostic Imaging and Storage (RADIS)
  Projected completion date: May 9th 2012
Lifecycle Phase: Coding
Project team
  Kelsey Hilton
  Austin Traverse
  Andrew McClellan

## Slide 4: Milestones Summary
Task | Projected Date | %Completion | On Time?
Use Cases | 3/30/2012 | 100% | Yes
UML Diagrams | 3/30/3012 | 100% | Yes
Constraints | 4/2/2012 | 100% | Yes
Requirements | 4/2/2012 | 100% | Yes
Project Plan | 4/6/2012 | 100% | No
UML Project | 4/9/2012 | 100% | Yes
Header Files | 4/16/2012 | 50% | No
Working Prototype | 4/20/2012 | 25% | No

## Slide 5: Outstanding Issues
This phase: Coding
CVIP is written in C so wrapper functions are necessary
CVIP is independent from Qt so there have to be Qt functions to connect the application to the API
Next phase: Testing
gTests may take extra formatting which takes time

## Slide 6: Status Review
Acceptance Status: Yellow Resource issues: Visual Studio Limitations, Qt Integration Concerns: Behind schedule Learning curve (gtests, Doxygen) Functionality left out e.g. image type support, database support, Visual Studio dependency

## Slide 7: Next Steps
Open issues -- GUI (Qt) not yet integrated with dA API(C++) Summary of status: Yellow Next phase: Testing Finding and formatting test data Writing user’s guide, tutorials and a thorough description of the API’s functionality Date for next project status review: May 9th 2012

## Slide 8
END